## Sheet1
Product Backlog
| User story | Strory potint | Acceptance Criteria | Tasks | Duration | Priority | Sprint | Calendar Date
1 | As a user, I want to be able to view and agree to the Privacy statement, so that I can use the app with confidence. | [5 empty] | 0
2 | As a new user, I want to be able to create an account and provide my basic information, so that I can use the app and connect with others. | [5 empty] | 0
3 | As a user, I want to be able to search for teams within a 5km distance, so that I can apply to join and connect with nearby teams. | [5 empty] | 0
4 | As a team member, I want to be able to start share my location with my team, so that we can coordinate and communicate effectively. | [5 empty] | 0
5 | As a team member, I want to be able to see the locations of other team members, so that I can coordinate with them effectively. | [5 empty] | 0
6 | As a team member, I want to be able to end the location sharing service at any time, so that I can protect my privacy. | [5 empty] | 0
7 | 7. As a team leader, I want to be able to transfer team leader position, and add or remove members, so that I can manage my team effectively.
8 | 8. As a user, I want to be able to create my own team and I can choose a team leader including myself, so that I can coordinate and manage the team.
9 | 9. As a team leader, I want to be able to set a meeting point for my team, so that we can easily find each other. | 2 | 1. The user interface should have an option for the team leader to set a meeting point. 2. The meeting point should be visible to all team members. 3. The meeting point should be marked on the map. 4. The meeting point should be easily accessible to team members. 5. The meeting point should be customizable and editable by the team leader. 6. The meeting point should be saved for future reference. | 1. Add a "Set Meeting Point" button to the user interface. 2. Implement the functionality to set the meeting point on the map. 3. Ensure that the meeting point is visible to all team members. 4. Implement a system to save and retrieve the meeting point data. 5. Add an option for the team leader to customize and edit the meeting point. 6. Test the meeting point functionality to ensure it meets the acceptance criteria. 7. Deploy the updated application to the production environment. | 1 week
10 | 10. As a team member, I want to be able to chat with other team members, so that we can communicate effectively and share information. | 4 | 1. The chat feature is integrated within the application. 2. Team members are able to send and receive messages with other members of their group. 3. Team members can create new chat groups and invite other members to join. 4. Messages are displayed in real-time and team members are notified of new messages. 5. Team members are able to delete or leave chat groups they no longer wish to be a part of. 6. The chat feature is intuitive and easy to use. | 1. Research and select a chat framework to integrate within the application. 2. Implement the chat feature within the application. 3. Allow users to create new chat groups and invite other users to join. 4. Implement real-time messaging and notifications 5. Allow users to delete or leave chat groups. 6. Test and debug the chat feature to ensure it is working properly. 7. Incorporate user feedback to improve the usability of the chat feature. | 2 weeks
11 | As a user, I want to be able to receive notifications when I am invited to join a team, so that I can stay informed. | 1 | 1. When invited to join a team, the user should receive a notification on their mobile device. 2. The notification should include the name of the team and a message inviting the user to join. 3. The notification should be clear and easy to understand, with a prominent call-to-action button to accept or decline the invitation. 4. If the user accepts the invitation, they should be directed to the team page within the app. 5. If the user declines the invitation, they should be removed from the invitation list and the team should be notified. | 1. Implement a notification system within the app that can send notifications to users. 2. Create a database schema for storing teams and team invitations. 3. Implement a user interface for sending invitations to join a team. 4. Implement logic for sending notifications to users when they are invited to join a team. 5. Implement a user interface for viewing and responding to team invitations. 6. Implement logic for accepting or declining team invitations. 7. Implement a user interface for viewing teams and team members. 8. Update the team page to show new members who have accepted invitations. | 3 days
12 | 12. As a team member, I want to be able to view the team's activity schedule, so that I can plan accordingly. | 4 | 1. The activity schedule should be accessible from the main menu of the application. 2. The activity schedule should display the date, time, location and description of each scheduled activity. 3. The activity schedule should be up-to-date and accurate, reflecting any changes or cancellations. 4. The activity schedule should be customizable, allowing users to add or remove activities as necessary. 5. The activity schedule should be easy to read and navigate, with a clear layout and font size. | 1. Determine the appropriate format and layout for the activity schedule. 2. Implement a new menu item for the activity schedule in the application's main menu. 3. Develop a data model for storing the activity schedule information. 4. Implement functionality to add, edit and delete activities in the schedule. 5. Integrate the activity schedule with the rest of the application's features and data. 6. Design and implement the user interface for the activity schedule, including a clear layout and font size. 7. Conduct testing and debugging to ensure that the activity schedule functions as intended and is free from errors. 8. Incorporate feedback from users and stakeholders to refine and improve the activity schedule. | 2 weeks
13 | 13. As a team member, I want to be able to see the team list and information like announcement, schedule, requirements etc, so that I can get all information I need.
14 | 14. As a user, I want to be able to easily delete my account, so that my personal information is no longer stored in the app.
15 | 15. As a user, I want to be able to search, add and delete friends on the app, so that I can connect with people I know.